## SCC List
Standard Cost Categories for ICR Core Capacity Projects
(Rev.26, January 2025)
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development
80.02 | Engineering
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES (CC Only)

## SCC Definitions
Standard Cost Categories for Core Capacity Projects D E F I N I T I O N S |  | NOTE: The SCC cost breakdown is based on a traditional Design Bid Build model. If your project is Design Build, to the best of your ability, separate construction costs from design, administration, testing, etc. Put all construction costs in 10 through 50. Put design, administration, testing, etc. in 80 Professional Services.
(Rev.26, January 2025) |  | Please note that 'green' shaded areas are locked by FTA and cannot be updated. Only 'white' cells within the body of the workbook (i.e., not outside the end of the workbook) should be used to enter project data. DO NOT alter the SCC workbook to create additional worksheets, without first speaking with FTA staff.
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | Include guideway and track costs for all transit modes (heavy rail, light rail, commuter rail, BRT, rapid bus, bus, monorail, cable car, etc.) The unit of measure is route miles of guideway, regardless of width. As associated with the guideway, include costs for rough grading, excavation, and concrete base for guideway where applicable. Include all construction materials and labor regardless of whom is performing the work. For example, if the project is constructing guideway 2 miles in one direction and 2 miles in the opposite direction, it should be noted as "2" miles in SCC 10, and the cost of constructing the guideway should be noted in its entirety. In your written description of the scope, and in supporting graphic diagrams, indicate whether busway or rail track is single, double, triple, relocated, etc. Put guideway and track elements associated with yards in 30 Support Facilities below.
10.01 | Guideway: At-grade exclusive right-of-way | BRT's: At-grade exclusive right-of-way that physically separates BRT vehicles from general traffic.
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | BRT's: At-grade designated traffic lane within a roadway mainly exclusive for the operation of BRT vehicles, other traffic can make turning movements through the dedicated lane.
10.03 | Guideway: At-grade in mixed traffic | BRTs: At-grade guideway not exclusive for BRT vehicles. Operates in mixed traffic within a roadway.
10.04 | Guideway: Aerial structure | Include foundation excavation; guideway structures including caissons, columns, bridges, viaducts, cross-overs, fly-overs. BRTs: Grade separated (Aerial structure) exclusive lane that physically separates BRT vehicles from other traffic
10.05 | Guideway: Built-up fill | Include construction of earthen berms.
10.06 | Guideway: Underground cut & cover | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.07 | Guideway: Underground tunnel | Include tunneling by means of a tunnel boring machine, drill blasting, mining, and immersed tube tunneling; tunnel structure and finishes.
10.08 | Guideway: Retained cut or fill | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.09 | Track: Direct fixation | Include rails, connectors.
10.1 | Track: Embedded | Include rails, ties; ballast where applicable
10.11 | Track: Ballasted | Include rails, ties and ballast.
10.12 | Track: Special (switches, turnouts) | Include transitional curves.
10.13 | Track: Vibration and noise dampening | Include upcharge for vib/noise dampening to any track condition above.
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | As associated with stations, include costs for rough grading, excavation, station structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, station power, lighting, public address/customer information system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include all construction materials and labor regardless of whom is performing the work. NOTE: Count paired inbound/outbound boarding platforms as one station - do not report the total number of boarding platforms.
Put guideway and track associated with stations in 10 Guideway & Track Elements above.
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform | Include station structures including caissons, columns, platforms, superstructures, etc.
20.03 | Underground station, stop, shelter, mall, terminal, platform | Include retaining walls, backfill, structure.
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development | Per FTA's Joint Development Guidance, "Joint development is any income-producing activity with a transit nexus related to a real estate asset in which FTA has an interest. ...Joint development projects are commercial, residential, industrial, or mixed-use developments that are induced by or enhance the effectiveness of transit projects. . ."
20.06 | Automobile parking multi-story structure | Include retaining walls, backfill, structure.
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | As associated with support facilities, include costs for rough grading, excavation, support structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, facility power, lighting, public address system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include fueling stations. Include bus charging equipment. Include all construction materials and labor regardless of whom is performing the work.
Where a support facility shares the structure with a station, its cost may be included with station cost. Identify this with a note.
Except for guideway and track associated with a yard, include all guideway and track costs associated with support facilities in 10 Guideway & Track Elements above.
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility | Include service, inspection, and storage facilities and equipment. Include costs for en-route charging equipment.
30.03 | Heavy Maintenance Facility | Include heavy maintenance and overhaul facilities and equipment.
30.04 | Storage or Maintenance of Way Building | Include costs for charging equipment located at end of route/terminal.
30.05 | Yard and Yard Track | Include yard construction, guideway and track associated with yard.
40 SITEWORK & SPECIAL CONDITIONS |  | Include all construction materials and labor regardless of whom is performing the work.
40.01 | Demolition, Clearing, Earthwork | Include project-wide clearing, demolition and fine grading.
40.02 | Site Utilities, Utility Relocation | Include all site utilities - storm, sewer, water, gas, electric.
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | Include underground storage tanks, fuel tanks, other hazardous materials and treatments, etc.
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | Include other environmental mitigation not listed.
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping | Include sidewalks, paths, plazas, functional landscaping, site and station furniture, site lighting, signage, bike facilities, permanent fencing.
40.07 | Automobile, bus, van accessways including roads, parking lots | Include all on-grade paving.
40.08 | Temporary Facilities and other indirect costs during construction | As a general rule and to the extent possible, appropriately allocate indirect costs among the construction costs in Categories 10 through 50. Where that is not possible, include in 40.08 Temporary Facilities costs for mobilization, demobilization, phasing; time and temporary construction associated with weather (heat, rain, freezing, etc.); temporary power and facilities; temporary construction, easements, and barriers for storm water pollution prevention, temporary access and to mitigate construction impacts; project and construction supervision; general conditions, overhead, profit. NOTE: Include contractor's general liability and other insurance related to construction such as builder's risk in Cats. 10 - 50, not in 80 Professional Services below.
50 SYSTEMS |  | Include all construction materials and labor regardless of whom is performing the work.
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection | Include signal prioritization at intersections.
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications | Include passenger information systems at stations and on vehicles (real time travel information; static maps and schedules). Include equipment to allow communications among vehicles and with central control.
50.06 | Fare collection system and equipment | Include fare sales and swipe machines, fare counting equipment.
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS |  | Include professional services associated with the real estate component of the project. These costs may include agency staff oversight and administration, real estate and relocation consultants, legal counsel, court expenses, insurance, etc.
60.01 | Purchase or lease of real estate | If the value of right-of-way, land, and existing improvements is to be used as local match to the Federal funding of the project, include the total cost on this line item. In backup documentation, separate cost for land from cost for improvements. Identify whether items are leased, purchased or acquired through payment or for free. Include the costs for permanent surface and subsurface easements, trackage rights, etc.
60.02 | Relocation of existing households and businesses | In compliance with Uniform Relocation Act.
70 VEHICLES (number) |  | Include professional services associated with the vehicle component of the project. These costs may include agency staff oversight and administration, vehicle consultants, design and manufacturing contractors, legal counsel, warranty and insurance costs, etc.
70.01 | Light Rail | Include light rail and streetcar rail using electric, diesel or other power supply.
70.02 | Heavy Rail
70.03 | Commuter Rail | Include locomotives (diesel, electric, or other), trailer cars, self-propelled multiple units (EMU electric or DMU diesel, or other power supply)
70.04 | Bus | Includes "rubber-tired" buses and trolleys including new, used, historic replica, articulated, using electric, diesel, dual-power, or other power supply.
70.05 | Other | Include Vans, Sedan/Station Wagon, Cable Car, People Mover, Monorail, Car/Inclined Railway, Ferry Boat, Transferred Vehicle
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | Cat. 80 applies to Cats. 10-50. Cat. 80 includes all professional, technical and management services related to the design and construction of fixed infrastructure (Cats. 10 - 50) during the project development and construction phases of the project. This includes environmental work, design, engineering and architectural services; specialty services such as safety or security analyses; value engineering, risk assessment, cost estimating, scheduling, ridership modeling and analyses, auditing, legal services, administration and management, etc. by agency staff or outside consultants. Include professional liability insurance and other non-construction insurance on 80.05 unless insurance for the agency and its consultants is already included in other lines. Include costs associated with professional services related to real estate and vehicles in Cats. 60 and 70. (Note that costs for planning activities and NEPA work done before FTA approval to enter project development (PD), regardless of funding source, are not included in an FFGA and therefore, should not be included in the Standard Cost Category worksheets. For example, on one and the same grant, costs incurred prior to FTA approval to enter PD should be omitted from these worksheets whereas costs incurred after FTA approval to enter PD should be included.) Include costs associated with before and after studies in 80.07
80.01 | Project Development
80.02 | Engineering
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up | Include start up and training. Include in Cats. 10 - 50 above access and protection work by agency staff or outside contractors.
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY |  | Includes unallocated contingency, project reserves. Document allocated contingencies for individual line items on the BUILD Main worksheet.
Subtotal (10 - 90)
100 FINANCE CHARGES (CC Only) |  | Include finance charges expected to be paid by the project sponsor/grantee prior to either the completion of the project or the fulfillment of the Core Capacity funding commitment, whichever occurs later in time. Finance charges incurred after this date should not be included in Total Project Cost. (See FFGA Circular FTA C5200.1A Chapter III for additional information.) Derive finance charges from the Core Capacity project's financial plan, based on an analysis of the sources and uses of funds. The amount and type of debt financing required and revenues available determine the finance charges. By year, compute finance charges in year-of-expenditure (YOE) dollars. On the Inflation worksheet enter the finance charges for the appropriate years.
Total Project Cost (10 - 100)

## TrAMS Scopes ALIs
14-Series TrAMS Scope / Activity Line Items Required for all grants that serve a Capital Project
(Rev.26, January 2025)
1. HOW DO THE SCC AND TrAMS RELATE? TrAMS is for grants management. Many grants can serve a capital project -- e.g. CMAQ, 5307, 5309, etc. The Standard Cost Categories (SCC) are for cost management practice at important milestones. To manage capital project costs use the SCC worksheets, back up sheets, detailed cost estimates, etc. At important milestones, "paperclip" the SCC worksheets to the applicable grants in TrAMS. TrAMS and the SCC support each. 2. WHEN SHOULD I USE THE 14-SERIES? Use it for capital projects. For a New Starts project, use it from the very first grant that funds Project Development, and include all grants issued through the FFGA; these grants may be small or large and may derive funding from diverse sources such as CMAQ, 5307, 5309 Capital Investment Grants, Federal Non-Transportation funding from HUD, Defense, etc. 3. HOW IS THE 14-SERIES ORGANIZED AND WHY? The 14-Series has one Scope and 10 ALIs. The organization is intentionally simple. Put guideway costs under the Guideway ALI, station costs under the Station ALI. If the costs are organized simply, the information will be consistent program-wide and will produce a reliable database. For Vehicles, use the 13-Series ALIs. | 140-00 | PROJECT NAME - (this is the one Scope)
| 14.01.10 | GUIDEWAY & TRACK ELEMENTS |  | .01 Bus STD 40 FT
.02 Bus STD 35 FT
.03 Bus 30 FT
| 14.02.20 | STATIONS, STOPS, TERMINALS, INTERMODAL |  | .04 Bus < 30 FT
.05 Bus School
.06 Bus Articulated
| 14.03.30 | SUPPORT FACILITIES: YARDS, SHOPS, ADMIN BLDGS |  | .07 Bus Commuter / Suburban
.08 Bus Intercity
.09 Bus Trolley STD
| 14.04.40 | SITEWORK & SPECIAL CONDITIONS | Engineering & Design | .10 Bus Trolley Artic.
|  |  | 13.11.XX | .11 Bus Double Deck
.12 Bus Used
| 14.05.50 | SYSTEMS | Purchase - Replacement | .13 Bus School Used
|  |  | 13.12.XX | .14 Bus Dual Mode
.15 Vans
| 14.06.60 | ROW, LAND, EXISTING IMPROVEMENTS | Purchase - Expansion | .16 Sedan / Station Wagon
|  |  | 13.13.XX | .20 Light Rail Cars
.21 Heavy Rail Cars
| 13____ | VEHICLES - use the 13-Series ALIs for vehicles. | Rehabilitation / Rebuild | .22 Commuter Rail Self Propelled Electric
|  |  | 13.14.XX | .23 Commuter Rail Car Trailer
.24 Commuter Rail Locomotive Diesel
| 14.08.80 | PROFESSIONAL SERVICES | Mid Life Rebuild (Rail) | .25 Commuter Rail Locomotive Electric
|  |  | 13.15.XX | .26 Commuter Rail Cars Used
.27 Commuter Rail Locomotive Used
| 14.09.90 | UNALLOCATED CONTINGENCY | Lease - Replacement | .28 Commuter Rail Self Propelled - Diesel
|  |  | 13.16.XX | .30 Cable Car
.31 People Mover
| 14.10.10 | FINANCE CHARGES | Lease - Expansion | .32 Car, Incline Railway
|  |  | 13.18.XX | .33 Ferry Boats
.39 Transferred Vehicles
|  |  | Vehicle Overhaul | .40 Spare Parts/Assoc.Capital
|  |  | 13.17.00 | / Maintenance Items

## Build Main
M A I N W O R K S H E E T - B U I L D A L T E R N A T I V E | [13 empty] | (Rev.26, January 2025)
Insert Project Sponsor's Name here | [9 empty] | Today's Date |  |  |  | 2026-08-04 21:52
Insert Project Name and Location | [9 empty] | Yr of Base Year $ |  |  |  | 2025
Insert Current Phase (e.g. Applic. for FFGA, Construction, Rev Ops) | [9 empty] | Yr of Revenue Ops |  |  |  | 2040
|  | Quantity | Base Year Dollars w/o Contingency (CC+SGR+ICR) (X000) | Base Year Dollars Allocated Contingency (CC+SGR+ICR) (X000) | Total Base Year Dollars (CC+SGR+ICR) (X000) | Core Capacity % (excluding SGR and intercity rail) | Base Year Dollars w/o Allocated Contingency (CC Only) | Base Year Dollars Allocated Contingency (CC Only) | Total Base Year Dollars (CC Only) | Total Base Year Dollars Percentage of Construction Cost | Total Base Year Dollars Percentage of Total Project Cost | Base Year Dollars (Core Capacity Only) Percentage of Total Project Cost | YOE Dollars (CC+SGR+ICR) (X000) | YOE Dollars (Core Capacity Only)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0!
10.01 | Guideway: At-grade exclusive right-of-way |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.03 | Guideway: At-grade in mixed traffic |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.04 | Guideway: Aerial structure |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.05 | Guideway: Built-up fill |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.06 | Guideway: Underground cut & cover |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.07 | Guideway: Underground tunnel |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.08 | Guideway: Retained cut or fill |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.09 | Track: Direct fixation |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.1 | Track: Embedded |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.11 | Track: Ballasted |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.12 | Track: Special (switches, turnouts) |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
10.13 | Track: Vibration and noise dampening |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0!
20.01 | At-grade station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
20.02 | Aerial station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
20.03 | Underground station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
20.05 | Joint development |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
20.06 | Automobile parking multi-story structure |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
20.07 | Elevators, escalators |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0!
30.01 | Administration Building: Office, sales, storage, revenue counting |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
30.02 | Light Maintenance Facility |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
30.03 | Heavy Maintenance Facility |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
30.04 | Storage or Maintenance of Way Building |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
30.05 | Yard and Yard Track |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
40 SITEWORK & SPECIAL CONDITIONS |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0!
40.01 | Demolition, Clearing, Earthwork |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
40.02 | Site Utilities, Utility Relocation |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
40.05 | Site structures including retaining walls, sound walls |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
40.06 | Pedestrian / bike access and accommodation, landscaping |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
40.07 | Automobile, bus, van accessways including roads, parking lots |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
40.08 | Temporary Facilities and other indirect costs during construction |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
50 SYSTEMS |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0!
50.01 | Train control and signals |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
50.02 | Traffic signals and crossing protection |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
50.03 | Traction power supply: substations |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
50.04 | Traction power distribution: catenary and third rail |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
50.05 | Communications |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
50.06 | Fare collection system and equipment |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
50.07 | Central Control |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
Construction Subtotal (10 - 50) |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0!
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0!
60.01 | Purchase or lease of real estate |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
60.02 | Relocation of existing households and businesses |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
70 VEHICLES (number) |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0!
70.01 | Light Rail |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
70.02 | Heavy Rail |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
70.03 | Commuter Rail |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
70.04 | Bus |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
70.05 | Other |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
70.06 | Non-revenue vehicles |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
70.07 | Spare parts |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0! | 0 | 0 | #DIV/0!
80.01 | Project Development |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
80.02 | Engineering |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
80.03 | Project Management for Design and Construction |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
80.04 | Construction Administration & Management |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
80.05 | Professional Liability and other Non-Construction Insurance |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
80.07 | Surveys, Testing, Investigation, Inspection |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
80.08 | Start up |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  | #DIV/0! | #DIV/0!
Subtotal (10 - 80) |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | #DIV/0! | #DIV/0! | 0 | 0
90 UNALLOCATED CONTINGENCY | [12 empty] | 0 | 0 | #DIV/0!
Subtotal (10 - 90) |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
100 FINANCE CHARGES (CC Only) |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | #DIV/0!
Total Project Cost (10 - 100) |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | #DIV/0!
Allocated Contingency as % of Base Yr Dollars w/o Contingency | [12 empty] | #DIV/0! | #DIV/0!
Unallocated Contingency as % of Base Yr Dollars w/o Contingency | [12 empty] | #DIV/0! | #DIV/0!
Total Contingency as % of Base Yr Dollars w/o Contingency | [12 empty] | #DIV/0! | #DIV/0!
Unallocated Contingency as % of Subtotal (10 - 80) | [12 empty] | #DIV/0! | #DIV/0!
YOE Construction Cost per Mile (X000) | [12 empty] | #DIV/0! | #DIV/0!
YOE Total Project Cost per Mile Not Including Vehicles (X000) | [12 empty] | #DIV/0! | #DIV/0!
YOE Total Project Cost per Mile (X000) | [12 empty] | #DIV/0! | #DIV/0!
Note on G6: Users manually enter these percentages
Note on I6: Green shaded areas are computed automatically. White cells should be used for manual entry
Note on L17: For each separate contract package generate a Main Worksheet and an Inflation Worksheet separately, and aggregate into this BUILD Main worksheet. Additional worksheets should be maintained for contract billing and reporting only. DO NOT alter the SCC workbook to create/insert additional worksheets. In the Special Conditions of the Contract, require the construction contractor to update these worksheets and submit them with the monthly pay application. This should make it easy to track costs in the SCC format throughout construction, and make it easy to submit the final costs to FTA at contract closeout.
Note on O3: Year of Base Year Dollars should match the year in "Today's Date."

## Inflation
I N F L A T I O N W O R K S H E E T |  |  | (Rev.26, January 2025)
Insert Project Sponsor's Name here |  |  | 2026-08-04 21:52
Insert Project Name and Location |  |  | 2025
Insert Current Phase (e.g. Applic. for FFGA, Construction, Rev Ops) |  |  | 2040
BASE YEAR DOLLARS (X$000) | Base Yr (CC+SGR) Dollars | Double-Check Total (CC+SGR) | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 0 | 0 | 2040 2012: 0; 2040 2013: 0; 2040 2014: 0; 2040 2015: 0; 2040 2016: 0; 2040 2017: 0; 2040 2018: 0; 2040 2019: 0; 2040 2020: 0; 2040 2021: 0; 2040 2022: 0; 2040 2023: 0; 2040 2024: 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 0 | 0 | 2040 2012: 0; 2040 2013: 0; 2040 2014: 0; 2040 2015: 0; 2040 2016: 0; 2040 2017: 0; 2040 2018: 0; 2040 2019: 0; 2040 2020: 0; 2040 2021: 0; 2040 2022: 0; 2040 2023: 0; 2040 2024: 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 0 | 0 | 2040 2012: 0; 2040 2013: 0; 2040 2014: 0; 2040 2015: 0; 2040 2016: 0; 2040 2017: 0; 2040 2018: 0; 2040 2019: 0; 2040 2020: 0; 2040 2021: 0; 2040 2022: 0; 2040 2023: 0; 2040 2024: 0
40 SITEWORK & SPECIAL CONDITIONS | 0 | 0 | 2040 2012: 0; 2040 2013: 0; 2040 2014: 0; 2040 2015: 0; 2040 2016: 0; 2040 2017: 0; 2040 2018: 0; 2040 2019: 0; 2040 2020: 0; 2040 2021: 0; 2040 2022: 0; 2040 2023: 0; 2040 2024: 0
50 SYSTEMS | 0 | 0 | 2040 2012: 0; 2040 2013: 0; 2040 2014: 0; 2040 2015: 0; 2040 2016: 0; 2040 2017: 0; 2040 2018: 0; 2040 2019: 0; 2040 2020: 0; 2040 2021: 0; 2040 2022: 0; 2040 2023: 0; 2040 2024: 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 0 | 0 | 2040 2012: 0; 2040 2013: 0; 2040 2014: 0; 2040 2015: 0; 2040 2016: 0; 2040 2017: 0; 2040 2018: 0; 2040 2019: 0; 2040 2020: 0; 2040 2021: 0; 2040 2022: 0; 2040 2023: 0; 2040 2024: 0
70 VEHICLES (number) | 0 | 0 | 2040 2012: 0; 2040 2013: 0; 2040 2014: 0; 2040 2015: 0; 2040 2016: 0; 2040 2017: 0; 2040 2018: 0; 2040 2019: 0; 2040 2020: 0; 2040 2021: 0; 2040 2022: 0; 2040 2023: 0; 2040 2024: 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 0 | 0 | 2040 2012: 0; 2040 2013: 0; 2040 2014: 0; 2040 2015: 0; 2040 2016: 0; 2040 2017: 0; 2040 2018: 0; 2040 2019: 0; 2040 2020: 0; 2040 2021: 0; 2040 2022: 0; 2040 2023: 0; 2040 2024: 0
90 UNALLOCATED CONTINGENCY | 0 | 0 | 2040 2012: 0; 2040 2013: 0; 2040 2014: 0; 2040 2015: 0; 2040 2016: 0; 2040 2017: 0; 2040 2018: 0; 2040 2019: 0; 2040 2020: 0; 2040 2021: 0; 2040 2022: 0; 2040 2023: 0; 2040 2024: 0
100 FINANCE CHARGES (CC Only) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Inflation Rate |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 1.035
Compounded Inflation Factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.035 | 1.0712 | 1.1087 | 1.1475 | 1.1877 | 1.2293 | 1.2723 | 1.3168 | 1.3629 | 1.4106 | 1.46 | 1.5111 | 1.564 | 1.6187 | 1.6753 | 1.734 | 1.7947 | 1.8575 | 1.9225 | 1.9898 | 2.0594 | 4.1909
YEAR OF EXPENDITURE DOLLARS (X$000) | YOE Dollars (CC+SGR) |  | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES (CC Only) | 0 |  | 2034: 0; 2035: 0; 2036: 0; 2037: 0; 2038: 0; 2039: 0; 2040: 0; 2041: 0; 2042: 0; 2043: 0; 2044: 0; 2045: 0; 2046: 0; 2047: 0
Total Project Cost (10 - 100) | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A33: Enter finance charges needed for the Core Capacity project only. Do not enter finance charges associated with SGR elements.
Note on I8: Because of inflation, it costs more to buy the same goods and services today than it would have cost in previous years. The total base year dollar cost is a concept that represents the total project cost if the project were planned, designed and built in only one year, the designated base year.
Note on R21: In the Base Year no inflation multiplier is used

## Project Description
P R O J E C T D E S C R I P T I O N - B U I L D A L T E R N A T I V E |  |  | (Rev.26, January 2025)
Insert Project Sponsor's Name here |  | Today's Date | 2026-08-04 21:52
Insert Project Name and Location
Insert Current Phase (e.g. Applic. for FFGA, Construction, Rev Ops)
Describe the project elements to explain the unit costs shown on the Main Worksheet. Example: A 20-mile new light rail project has its guideway entirely on grade except for a one-eighth mile bridge over a river. The bridge or aerial structure may have a relatively high unit cost because there is little economy of scale. Mention precedents and reference points used in the development of costs for this project. Mention other aspects of this project that were important considerations in estimating costs. These could include the physical context, site constraints; design parameters; institutional, contracting and procurement conditions; project schedule, etc.
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Project Development
80.02 | Engineering
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY
Subtotal (10 - 90)
100 FINANCE CHARGES (CC Only)
Total Project Cost (10 - 100)
Note on C8: These rows can be expanded to fit your narrative. Delete lines that are not needed.
Note on C27: For each garage, list station name, number of floors above and below grade, and number of spaces in each garage
Note on C42: For each parking lot, list station name and number of spaces

## Schedule FFGA A4
S C H E D U L E |  |  | (Rev.26, January 2025)
Insert Project Sponsor's Name here | Today's Date |  | 2026-08-04 21:52
Insert Project Name and Location | Yr of Base Year $ |  | 2025
Insert Current Phase (e.g. Applic. for FFGA, Construction, Rev Ops) | Yr of Revenue Ops |  | 2040
|  | Start Date | End Date | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
10 GUIDEWAY & TRACK ELEMENTS (route miles)
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
40 SITEWORK & SPECIAL CONDITIONS
50 SYSTEMS
60 ROW, LAND, EXISTING IMPROVEMENTS
70 VEHICLES (number)
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES
REVENUE OPERATIONS (Expanded Service begins)
BEFORE AND AFTER STUDIES
FULLFILLMENT OF THE CORE CAPACITY FUNDING COMMITMENT
COMPLETION OF PROJECT CLOSE-OUT
Note on C7: On this Schedule and on the Inflation Worksheet, indicate the start of PD with the date of FTA's letter granting entry into PD. Delete any rows that are not needed
Note on E6: Delete years that are not applicable.

## Build Annualized
A N N U A L I Z E D C O S T - B U I L D A L T E R N A T I V E (Current Year) | [9 empty] | (Rev.26, January 2025)
Insert Project Sponsor's Name here | [7 empty] | Today's Date |  | 2026-08-04 21:52
Insert Project Name and Location | [7 empty] | Yr of Base Year $ |  | 2025
Insert Current Phase (e.g. Applic. for FFGA, Construction, Rev Ops) | [7 empty] | Yr of Revenue Ops |  | 2040
|  | Quantity | Base Year Core Capacity Dollars (X000) | Cat. 80 Prof. Svc. spread proportionally over Cats. 10 - 50 (X000) | Spread Cat. 90 Unalloc. Cont. according to perceived risks (X000) | Revised Total Base Year Dollars (X000) | #DIV/0! | Years of Useful Life | Annualization Factor (based on 2% rate) [.02/1 - (1.02)^-no. yrs] | Annualized Core Capacity Share (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 0 | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! |  |  | #DIV/0!
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 125 | 0.021837 | #DIV/0!
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 30 | 0.04465 | #DIV/0!
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 20 | 0.061157 | #DIV/0!
10.04 | Guideway: Aerial structure | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 80 | 0.025161 | #DIV/0!
10.05 | Guideway: Built-up fill | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 80 | 0.025161 | #DIV/0!
10.06 | Guideway: Underground cut & cover | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 125 | 0.021837 | #DIV/0!
10.07 | Guideway: Underground tunnel | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 125 | 0.021837 | #DIV/0!
10.08 | Guideway: Retained cut or fill | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 125 | 0.021837 | #DIV/0!
10.09 | Track: Direct fixation |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 30 | 0.04465 | #DIV/0!
10.1 | Track: Embedded |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 20 | 0.061157 | #DIV/0!
10.11 | Track: Ballasted |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 35 | 0.040002 | #DIV/0!
10.12 | Track: Special (switches, turnouts) |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 30 | 0.04465 | #DIV/0!
10.13 | Track: Vibration and noise dampening |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 30 | 0.04465 | #DIV/0!
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 0 | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! |  |  | #DIV/0!
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 0 | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 70 | 0.026668 | #DIV/0!
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 70 | 0.026668 | #DIV/0!
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 125 | 0.021837 | #DIV/0!
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 70 | 0.026668 | #DIV/0!
20.05 | Joint development |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 70 | 0.026668 | #DIV/0!
20.06 | Automobile parking multi-story structure |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 50 | 0.031823 | #DIV/0!
20.07 | Elevators, escalators |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 30 | 0.04465 | #DIV/0!
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! |  |  | #DIV/0!
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 50 | 0.031823 | #DIV/0!
30.02 | Light Maintenance Facility |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 50 | 0.031823 | #DIV/0!
30.03 | Heavy Maintenance Facility |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 50 | 0.031823 | #DIV/0!
30.04 | Storage or Maintenance of Way Building |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 50 | 0.031823 | #DIV/0!
30.05 | Yard and Yard Track |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! | 80 | 0.025161 | #DIV/0!
40 SITEWORK & SPECIAL CONDITIONS |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! |  |  | #DIV/0!
40.01 | Demolition, Clearing, Earthwork |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 125 | 0.021837 | #DIV/0!
40.02 | Site Utilities, Utility Relocation |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 125 | 0.021837 | #DIV/0!
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 125 | 0.021837 | #DIV/0!
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 125 | 0.021837 | #DIV/0!
40.05 | Site structures including retaining walls, sound walls |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 80 | 0.025161 | #DIV/0!
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 20 | 0.061157 | #DIV/0!
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 20 | 0.061157 | #DIV/0!
40.08 | Temporary Facilities and other indirect costs during construction |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 100 | 0.023203 | #DIV/0!
50 SYSTEMS |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! |  |  | #DIV/0!
50.01 | Train control and signals |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 30 | 0.04465 | #DIV/0!
50.02 | Traffic signals and crossing protection |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 30 | 0.04465 | #DIV/0!
50.03 | Traction power supply: substations |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 50 | 0.031823 | #DIV/0!
50.04 | Traction power distribution: catenary and third rail |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 30 | 0.04465 | #DIV/0!
50.05 | Communications |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 20 | 0.061157 | #DIV/0!
50.06 | Fare collection system and equipment |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 25 | 0.05122 | #DIV/0!
50.07 | Central Control |  | 0 | #DIV/0! |  | #DIV/0! | #DIV/0! | 30 | 0.04465 | #DIV/0!
Construction Subtotal (10 - 50) |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! |  |  | #DIV/0!
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 0 |  | 0 | 0 | #DIV/0! |  |  | #DIV/0!
60.01 | Purchase or lease of real estate |  | 0 |  |  | 0 | #DIV/0! | 125 | 0.021837 | #DIV/0!
60.02 | Relocation of existing households and businesses |  | 0 |  |  | 0 | #DIV/0! | 125 | 0.021837 | #DIV/0!
70 VEHICLES (number) |  | 0 | 0 |  | 0 | 0 | #DIV/0! |  |  | #DIV/0!
70.01 | Light Rail | 0 | 0 |  | 0 | 0 | #DIV/0! | 25 | 0.05122 | #DIV/0!
70.02 | Heavy Rail | 0 | 0 |  | 0 | 0 | #DIV/0! | 25 | 0.05122 | #DIV/0!
70.03 | Commuter Rail | 0 | 0 |  | 0 | 0 | #DIV/0! | 25 | 0.05122 | #DIV/0!
70.04 | Bus | 0 | 0 |  | 0 | 0 | #DIV/0! | 12 | 0.09456 | #DIV/0!
70.05 | Other | 0 | 0 |  | 0 | 0 | #DIV/0! | 12 | 0.09456 | #DIV/0!
70.06 | Non-revenue vehicles | 0 | 0 |  | 0 | 0 | #DIV/0! | 12 | 0.09456 | #DIV/0!
70.07 | Spare parts | 0 | 0 |  | 0 | 0 | #DIV/0! | 12 | 0.09456 | #DIV/0!
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  |  | 0
80.01 | Project Development |  | 0
80.02 | Engineering |  | 0
80.03 | Project Management for Design and Construction |  | 0
80.04 | Construction Administration & Management |  | 0
80.05 | Professional Liability and other Non-Construction Insurance |  | 0
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 0
80.07 | Surveys, Testing, Investigation, Inspection |  | 0
80.08 | Start up |  | 0
Subtotal (10 - 80) |  |  | 0
90 UNALLOCATED CONTINGENCY |  |  | 0
TOTAL |  |  | 0 | #DIV/0! | 0 | #DIV/0! | #DIV/0! |  |  | #DIV/0!
Note on E75: E75 and F75 are double-checks
Note on I60: The range for buses is 12 to 18 years. Provide supporting documentation for an estimated useful life of more than 12 years.

## Fund Source by Cat
F U N D I N G S O U R C E S B Y C A T E G O R Y | [10 empty] | (Rev.26, January 2025)
Insert Project Sponsor's Name here | [9 empty] | Today's Date | 2026-08-04 21:52
Insert Project Name and Location
Insert Current Phase (e.g. Applic. for FFGA, Construction, Rev Ops)
| Cost |  | Funding Summary |  |  | Federal Sources |  | Local Sources
| YOE Core Capacity Cost (X000) | Double- check Total | Federal 5309 Core Capacity | Federal Other Funds | Local Funds | Federal 5309 Core Capacity | Federal Other | Sales Tax | Other | Other | Other | Other
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES (CC Only) | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Percentage of Total Project Cost | 100% |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | #DIV/0! | #DIV/0!
#DIV/0!
Note on H6: DO NOT include State of Good Repair Funds in this area.
Note on J6: Insert additional columns as required.

## Fund Source by Year
F U N D I N G S O U R C E S B Y Y E A R CC PROJECT | [5 empty] | (Rev.26, January 2025)
Insert Project Sponsor's Name here |  |  | Today's Date | 2026-08-04 21:52
Insert Project Name and Location
Insert Current Phase (e.g. Applic. for FFGA, Construction, Rev Ops)
| Double-check total | Total All Years | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
Federal 5309 Core Capacity |  | 0
Local |  | 0
Federal Other |  | 0
Total Project Cost (10 - 100) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on M6: The information reported below should match what is reported in the financial plan. FTA uses this data to get an understanding of future demand for Section 5309 funds. The inputs should not assume Section 5309 funding in fiscal years for which appropriations have already occurred and the project did not receive anything.

## FFGA A3T1
BCE by Standard Cost Category
Applicable Line Items Only |  | YOE Dollars
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 0
10.01 | Guideway: At-grade exclusive right-of-way | #DIV/0!
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | #DIV/0!
10.03 | Guideway: At-grade in mixed traffic | #DIV/0!
10.04 | Guideway: Aerial structure | #DIV/0!
10.05 | Guideway: Built-up fill | #DIV/0!
10.06 | Guideway: Underground cut & cover | #DIV/0!
10.07 | Guideway: Underground tunnel | #DIV/0!
10.08 | Guideway: Retained cut or fill | #DIV/0!
10.09 | Track: Direct fixation | #DIV/0!
10.1 | Track: Embedded | #DIV/0!
10.11 | Track: Ballasted | #DIV/0!
10.12 | Track: Special (switches, turnouts) | #DIV/0!
10.13 | Track: Vibration and noise dampening | #DIV/0!
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 0
20.01 | At-grade station, stop, shelter, mall, terminal, platform | #DIV/0!
20.02 | Aerial station, stop, shelter, mall, terminal, platform | #DIV/0!
20.03 | Underground station, stop, shelter, mall, terminal, platform | #DIV/0!
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | #DIV/0!
20.05 | Joint development | #DIV/0!
20.06 | Automobile parking multi-story structure | #DIV/0!
20.07 | Elevators, escalators | #DIV/0!
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 0
30.01 | Administration Building: Office, sales, storage, revenue counting | #DIV/0!
30.02 | Light Maintenance Facility | #DIV/0!
30.03 | Heavy Maintenance Facility | #DIV/0!
30.04 | Storage or Maintenance of Way Building | #DIV/0!
30.05 | Yard and Yard Track | #DIV/0!
40 SITEWORK & SPECIAL CONDITIONS |  | 0
40.01 | Demolition, Clearing, Earthwork | #DIV/0!
40.02 | Site Utilities, Utility Relocation | #DIV/0!
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | #DIV/0!
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | #DIV/0!
40.05 | Site structures including retaining walls, sound walls | #DIV/0!
40.06 | Pedestrian / bike access and accommodation, landscaping | #DIV/0!
40.07 | Automobile, bus, van accessways including roads, parking lots | #DIV/0!
40.08 | Temporary Facilities and other indirect costs during construction | #DIV/0!
50 SYSTEMS |  | 0
50.01 | Train control and signals | #DIV/0!
50.02 | Traffic signals and crossing protection | #DIV/0!
50.03 | Traction power supply: substations | #DIV/0!
50.04 | Traction power distribution: catenary and third rail | #DIV/0!
50.05 | Communications | #DIV/0!
50.06 | Fare collection system and equipment | #DIV/0!
50.07 | Central Control | #DIV/0!
Construction Subtotal (10 - 50) |  | 0
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 0
60.01 | Purchase or lease of real estate | #DIV/0!
60.02 | Relocation of existing households and businesses | #DIV/0!
70 VEHICLES (number) |  | 0
70.01 | Light Rail | #DIV/0!
70.02 | Heavy Rail | #DIV/0!
70.03 | Commuter Rail | #DIV/0!
70.04 | Bus | #DIV/0!
70.05 | Other | #DIV/0!
70.06 | Non-revenue vehicles | #DIV/0!
70.07 | Spare parts | #DIV/0!
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 0
80.01 | Project Development | #DIV/0!
80.02 | Engineering | #DIV/0!
80.03 | Project Management for Design and Construction | #DIV/0!
80.04 | Construction Administration & Management | #DIV/0!
80.05 | Professional Liability and other Non-Construction Insurance | #DIV/0!
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | #DIV/0!
80.07 | Surveys, Testing, Investigation, Inspection | #DIV/0!
80.08 | Start up | #DIV/0!
Subtotal (10 - 80) |  | 0
90 UNALLOCATED CONTINGENCY |  | 0
Subtotal (10 - 90) |  | 0
100 FINANCE CHARGES (CC Only) |  | 0
Total Project Cost (10 - 100) |  | 0
Note on B1: This sheet, FFGA A3T1, and the sheets that follow become Attachments to the FFGA
Note on B3: Delete rows that are not needed.

## FFGA A3T2
Inflated Cost to Year of Expenditure
| Base Year Dollars w/o Contingency | Base Year Dollars Allocated Contingency | Base Year Dollars TOTAL | Inflation Factor | YOE Dollars TOTAL
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 0 | 0 | 0 | #DIV/0! | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 0 | 0 | 0 | #DIV/0! | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 0 | 0 | 0 | #DIV/0! | 0
40 SITEWORK & SPECIAL CONDITIONS | 0 | 0 | 0 | #DIV/0! | 0
50 SYSTEMS | 0 | 0 | 0 | #DIV/0! | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 0 | 0 | 0 | #DIV/0! | 0
70 VEHICLES (number) | 0 | 0 | 0 | #DIV/0! | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 0 | 0 | 0 | #DIV/0! | 0
90 UNALLOCATED CONTINGENCY |  |  | 0 | #DIV/0! | 0
100 FINANCE CHARGES (CC Only) |  |  | 0 | #DIV/0! | 0
Total Project Cost (10 - 100) |  |  | 0 | #DIV/0! | 0
Note on G3: Delete rows that are not needed.

## FFGA A3T3
BCE by Source of Funding
| Total Project Cost in YOE Dollars | Double Check Total | Federal 5309 Core Capacity | Federal Other: CMAQ | Local
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES (CC Only) | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 0 | 0 | 0 | 0 | 0
Sources of Federal Funding and Matching Share Ratios
| Costs Attributed to Source of Funds | Federal/ Local Matching Ratio within Source | All Federal Funds | Local Funds
Federal 5309 Core Capacity | 0 | 0
Federal: Other (please specify sources...) | 0 | 0
Federal: Other (please specify sources...) | 0 | 0
Federal: Other (please specify sources...) | 0 | 0
Total | 0 |  | 0 | 0
Overall Federal Share of Project |  |  | #DIV/0!
Core Capacity Share of Project |  |  | #DIV/0!
Note on A3: Delete rows that are not needed
Note on A21: Add rows as needed to show all federal funding

## FFGA A3A
Scope and Activity Description
Scope Code | ALI Code | Scope and Activity Line Item Descriptions | Qty |  | Federal 5309 Core Capacity |  |  | Federal Other |  |  | Project Totals |  |  | Check Total Project Cost in YOE Dollars
|  |  |  | Total Federal % | Federal | Local | Total | Federal | Local | Total | Federal | Local | Total
14010 | 140110 | GUIDEWAY & TRACK ELEMENTS | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14020 | 140220 | STATIONS, STOPS, TERMINALS, INTERMODAL | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14030 | 140330 | SUPPORT FACILITIES, YARDS, SHOPS, ADMIN. BLDGS. |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14040 | 140440 | SITEWORK & SPECIAL CONDITIONS |  | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14050 | 140550 | SYSTEMS |  | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14060 | 140660 | ROW, LAND, EXISTING IMPROVEMENTS |  | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14070 |  | VEHICLES | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 13.13.20 | COMMUTER RAIL VEHICLES
14080 | 140880 | PROFESSIONAL SERVICES |  | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14090 | 140990 | UNALLOCATED CONTINGENCY |  | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14100 | 141010 | FINANCE CHARGES |  | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) |  |  |  | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Note on C4: Delete rows that are not needed.
Note on I2: Add more tri-columns as required to show all funding.