## SCC List
Standard Cost Categories for Capital Projects
(Rev.14, August 5, 2011)
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Preliminary Engineering
80.02 | Final Design
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES

## SCC Definitions
Standard Cost Categories for Capital Projects D E F I N I T I O N S |  | NOTE: The SCC cost breakdown is based on a traditional Design Bid Build model. If your project is Design Build, to the best of your ability, separate construction costs from design, administration, testing, etc. Put all construction costs in 10 through 50. Put design, administration, testing, etc. in 80 Professional Services.
(Rev.14, August 5, 2011)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | Include guideway and track costs for all transit modes (Heavy rail, light rail, commuter rail, BRT, rapid bus, bus, monorail, cable car, etc.) The unit of measure is route miles of guideway, regardless of width. As associated with the guideway, include costs for rough grading, excavation, and concrete base for guideway where applicable. Include all construction materials and labor regardless of whom is performing the work. In your written description of the scope and in supporting graphic diagrams, indicate whether busway or rail track is single, double, triple, relocated, etc. Put guideway and track elements associated with yards in 30 Support Facilities below.
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure | Include foundation excavation; guideway structures including caissons, columns, bridges, viaducts, cross-overs, fly-overs.
10.05 | Guideway: Built-up fill | Include construction of earthen berms.
10.06 | Guideway: Underground cut & cover | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.07 | Guideway: Underground tunnel | Include tunneling by means of a tunnel boring machine, drill blasting, mining, and immersed tube tunneling; tunnel structure and finishes.
10.08 | Guideway: Retained cut or fill | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.09 | Track: Direct fixation | Include rails, connectors.
10.1 | Track: Embedded | Include rails, ties; ballast where applicable
10.11 | Track: Ballasted | Include rails, ties and ballast.
10.12 | Track: Special (switches, turnouts) | Include transitional curves.
10.13 | Track: Vibration and noise dampening | Include upcharge for vib/noise dampening to any track condition above.
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | As associated with stations, include costs for rough grading, excavation, station structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, station power, lighting, public address/customer information system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include all construction materials and labor regardless of whom is performing the work.
Put guideway and track associated with stations in 10 Guideway & Track Elements above.
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform | Include station structures including caissons, columns, platforms, superstructures, etc.
20.03 | Underground station, stop, shelter, mall, terminal, platform | Include retaining walls, backfill, structure.
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development | Per FTA's Joint Development Guidance, "Joint development is any income-producing activity with a transit nexus related to a real estate asset in which FTA has an interest. . .Joint development projects are commercial, residential, industrial, or mixed-use developments that are induced by or enhance the effectiveness of transit projects. . ."
20.06 | Automobile parking multi-story structure | Include retaining walls, backfill, structure.
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | As associated with support facilities, include costs for rough grading, excavation, support structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, facility power, lighting, public address system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include fueling stations. Include all construction materials and labor regardless of whom is performing the work.
Where a support facility shares the structure with a station, its cost may be included with station cost. Identify this with a note.
Except for guideway and track associated with a yard, include all guideway and track costs associated with support facilities in 10 Guideway & Track Elements above.
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility | Include service, inspection, and storage facilities and equipment.
30.03 | Heavy Maintenance Facility | Include heavy maintenance and overhaul facilities and equipment.
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track | Include yard construction, guideway and track associated with yard.
40 SITEWORK & SPECIAL CONDITIONS |  | Include all construction materials and labor regardless of whom is performing the work.
40.01 | Demolition, Clearing, Earthwork | Include project-wide clearing, demolition and fine grading.
40.02 | Site Utilities, Utility Relocation | Include all site utilities - storm, sewer, water, gas, electric.
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | Include underground storage tanks, fuel tanks, other hazardous materials and treatments, etc.
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | Include other environmental mitigation not listed.
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping | Include sidewalks, paths, plazas, landscape, site and station furniture, site lighting, signage, public artwork, bike facilities, permanent fencing.
40.07 | Automobile, bus, van accessways including roads, parking lots | Include all on-grade paving.
40.08 | Temporary Facilities and other indirect costs during construction | As a general rule and to the extent possible, appropriately allocate indirect costs among the construction costs in Categories 10 through 50. Where that is not possible, include in 40.08 Temporary Facilities costs for mobilization, demobilization, phasing; time and temporary construction associated with weather (heat, rain, freezing, etc.); temporary power and facilities; temporary construction, easements, and barriers for storm water pollution prevention, temporary access and to mitigate construction impacts; project and construction supervision; general conditions, overhead, profit. NOTE: Include contractor's general liability and other insurance related to construction such as builder's risk in Cats. 10 - 50, not in 80 Professional Services below.
50 SYSTEMS |  | Include all construction materials and labor regardless of whom is performing the work.
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection | Include signal prioritization at intersections.
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications | Include passenger information systems at stations and on vehicles (real time travel information; static maps and schedules). Include equipment to allow communications among vehicles and with central control.
50.06 | Fare collection system and equipment | Include fare sales and swipe machines, fare counting equipment.
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS |  | Include professional services associated with the real estate component of the project. These costs may include agency staff oversight and administration, real estate and relocation consultants, legal counsel, court expenses, insurance, etc.
60.01 | Purchase or lease of real estate | If the value of right-of-way, land, and existing improvements is to be used as local match to the Federal funding of the project, include the total cost on this line item. In backup documentation, separate cost for land from cost for improvements. Identify whether items are leased, purchased or acquired through payment or for free. Include the costs for permanent surface and subsurface easements, trackage rights, etc.
60.02 | Relocation of existing households and businesses | In compliance with Uniform Relocation Act.
70 VEHICLES (number) |  | Include professional services associated with the vehicle component of the project. These costs may include agency staff oversight and administration, vehicle consultants, design and manufacturing contractors, legal counsel, warranty and insurance costs, etc.
70.01 | Light Rail | Include light rail and streetcar rail using electric, diesel or other power supply.
70.02 | Heavy Rail
70.03 | Commuter Rail | Include locomotives (diesel, electric, or other), trailer cars, self-propelled multiple units (EMU electric or DMU diesel, or other power supply)
70.04 | Bus | Includes "rubber-tired" buses and trolleys including new, used, historic replica, articulated, using electric, diesel, dual-power, or other power supply.
70.05 | Other | Include Vans, Sedan/Station Wagon, Cable Car, People Mover, Monorail, Car/Inclined Railway, Ferry Boat, Transferred Vehicle
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | Cat. 80 applies to Cats. 10-50. Cat. 80 includes all professional, technical and management services related to the design and construction of fixed infrastructure (Cats. 10 - 50) during the preliminary engineering, final design, and construction phases of the project. This includes environmental work, design, engineering and architectural services; specialty services such as safety or security analyses; value engineering, risk assessment, cost estimating, scheduling, Before and After studies, ridership modeling and analyses, auditing, legal services, administration and management, etc. by agency staff or outside consultants. Include professional liability insurance and other non-construction insurance on 80.05 unless insurance for the agency and its consultants is already included in other lines. Include costs associated with professional services related to real estate and vehicles in Cats. 60 and 70. (Note that costs for alternatives analysis and NEPA work done before FTA approval to enter preliminary engineering (PE), regardless of funding source, are not included in an FFGA and therefore, should not be included in the Standard Cost Category worksheets. For example, on one and the same grant, costs incurred prior to FTA approval to enter PE should be omitted from these worksheets whereas costs incurred after FTA approval to enter PE should be included.)
80.01 | Preliminary Engineering
80.02 | Final Design
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up | Include start up and training. Include in Cats. 10 - 50 above access and protection work by agency staff or outside contractors.
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY |  | Includes unallocated contingency, project reserves. Document allocated contingencies for individual line items on the Main worksheets.
Subtotal (10 - 90)
100 FINANCE CHARGES |  | Include finance charges expected to be paid by the project sponsor/grantee prior to either the completion of the project or the fulfillment of the New Starts funding commitment, whichever occurs later in time. Finance charges incurred after this date should not be included in Total Project Cost. (See FFGA Circular FTA C5200.1A Chapter III for additional information.) Derive finance charges from the New Starts project's financial plan, based on an analysis of the sources and uses of funds. The amount and type of debt financing required and revenues available determine the finance charges. By year, compute finance charges in year-of-expenditure (YOE) dollars. On the Inflation Calculation to YOE worksheet enter the finance charges for the appropriate years.
Total Project Cost (10 - 100)

## TEAM Scopes ALIs
14-Series TEAM Scope / Activity Line Items Required for all grants that serve a Capital Project
(Rev.14, August 5, 2011)
1. HOW DO THE SCC AND TEAM RELATE? TEAM is for grants management. Many grants can serve a capital project -- e.g. CMAQ, 5307, 5309, etc. The Standard Cost Categories (SCC) are for cost management, day to day as well as at important milestones. To manage capital project costs use the SCC worksheets, back up sheets, detailed cost estimates, etc. At important milestones, "paperclip" the SCC worksheets to the applicable grants in TEAM. TEAM and the SCC support each other but TEAM doesn't duplicate the level of information in the SCC. Grant budgets will have just the ten lines. 2. WHEN SHOULD I USE THE 14-SERIES? Use it for capital projects. For a New Starts project, use it from the very first grant that funds Preliminary Engineering, and include all grants issued through the FFGA; these grants may be small or large and may derive funding from diverse sources such as CMAQ, 5307, 5309 Fixed Guideway Mod, 5309 New Starts, Federal Non-Transportation funding from HUD, Defense, etc. 3. HOW IS THE 14-SERIES ORGANIZED AND WHY? The 14-Series has one Scope and 10 ALIs. The organization is intentionally simple. Put guideway costs under the Guideway ALI, station costs under the Station ALI. If the costs are organized simply, the information will be consistent program-wide and will produce a reliable database. For Vehicles, use the 13-Series ALIs. | 140-00 | PROJECT NAME - (this is the one Scope)
| 14.01.10 | GUIDEWAY & TRACK ELEMENTS |  | .01 Bus STD 40 FT
.02 Bus STD 35 FT
.03 Bus 30 FT
| 14.02.20 | STATIONS, STOPS, TERMINALS, INTERMODAL |  | .04 Bus < 30 FT
.05 Bus School
.06 Bus Articulated
| 14.03.30 | SUPPORT FACILITIES: YARDS, SHOPS, ADMIN BLDGS |  | .07 Bus Commuter / Suburban
.08 Bus Intercity
.09 Bus Trolley STD
| 14.04.40 | SITEWORK & SPECIAL CONDITIONS | Engineering & Design | .10 Bus Trolley Artic.
|  |  | 13.11.XX | .11 Bus Double Deck
.12 Bus Used
| 14.05.50 | SYSTEMS | Purchase - Replacement | .13 Bus School Used
|  |  | 13.12.XX | .14 Bus Dual Mode
.15 Vans
| 14.06.60 | ROW, LAND, EXISTING IMPROVEMENTS | Purchase - Expansion | .16 Sedan / Station Wagon
|  |  | 13.13.XX | .20 Light Rail Cars
.21 Heavy Rail Cars
| 13____ | VEHICLES - use the 13-Series ALIs for vehicles. | Rehabilitation / Rebuild | .22 Commuter Rail Self Propelled Electric
|  |  | 13.14.XX | .23 Commuter Rail Car Trailer
.24 Commuter Rail Locomotive Diesel
| 14.08.80 | PROFESSIONAL SERVICES | Mid Life Rebuild (Rail) | .25 Commuter Rail Locomotive Electric
|  |  | 13.15.XX | .26 Commuter Rail Cars Used
.27 Commuter Rail Locomotive Used
| 14.09.90 | UNALLOCATED CONTINGENCY | Lease - Replacement | .28 Commuter Rail Self Propelled - Diesel
|  |  | 13.16.XX | .30 Cable Car
.31 People Mover
| 14.10.10 | FINANCE CHARGES | Lease - Expansion | .32 Car, Incline Railway
|  |  | 13.18.XX | .33 Ferry Boats
.39 Transferred Vehicles
|  |  | Vehicle Overhaul | .40 Spare Parts/Assoc.Capital
|  |  | 13.17.00 | / Maintenance Items

## BUILD Main
M A I N W O R K S H E E T - B U I L D A L T E R N A T I V E | [8 empty] | (Rev.14, August 5, 2011)
Insert Project Sponsor's Name here | [6 empty] | Today's Date |  | 2011-08-05
Insert Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2011
Insert Current Phase (e.g. Applic.for PE, PE, FD, Applic. for FFGA, Construction, Rev Ops) | [6 empty] | Yr of Revenue Ops |  | 2020
|  | Quantity | Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Base Year Dollars Unit Cost (X000) | Base Year Dollars Percentage of Construction Cost | Base Year Dollars Percentage of Total Project Cost | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 10 | 80000000 | 20000000 | 100000000 | 10000000 | 44.77% | 25.37% | 104780125 | 1.0478
10.01 | Guideway: At-grade exclusive right-of-way | 10 | 80000000 | 20000000 | 100000000 | 10000000 |  |  | 104780125
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) |  |  |  | 0 |  |  |  | 0
10.03 | Guideway: At-grade in mixed traffic |  |  |  | 0 |  |  |  | 0
10.04 | Guideway: Aerial structure |  |  |  | 0 |  |  |  | 0
10.05 | Guideway: Built-up fill |  |  |  | 0 |  |  |  | 0
10.06 | Guideway: Underground cut & cover |  |  |  | 0 |  |  |  | 0
10.07 | Guideway: Underground tunnel |  |  |  | 0 |  |  |  | 0
10.08 | Guideway: Retained cut or fill |  |  |  | 0 |  |  |  | 0
10.09 | Track: Direct fixation |  |  |  | 0 |  |  |  | 0
10.1 | Track: Embedded |  |  |  | 0 |  |  |  | 0
10.11 | Track: Ballasted |  |  |  | 0 |  |  |  | 0
10.12 | Track: Special (switches, turnouts) |  |  |  | 0 |  |  |  | 0
10.13 | Track: Vibration and noise dampening |  |  |  | 0 |  |  |  | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 20 | 28000000 | 2000000 | 30000000 | 1500000 | 13.43% | 7.612% | 32149428.75 | 1.0716
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 20 | 28000000 | 2000000 | 30000000 | 1500000 |  |  | 32149428.75
20.02 | Aerial station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. |  |  |  | 0 |  |  |  | 0
20.05 | Joint development |  |  |  | 0 |  |  |  | 0
20.06 | Automobile parking multi-story structure |  |  |  | 0 |  |  |  | 0
20.07 | Elevators, escalators |  |  |  | 0 |  |  |  | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 10 | 8000000 | 2000000 | 10000000 | 1000000 | 4.477% | 2.537% | 10531125 | 1.0531
30.01 | Administration Building: Office, sales, storage, revenue counting |  |  |  | 0 |  |  |  | 0
30.02 | Light Maintenance Facility |  | 8000000 | 2000000 | 10000000 |  |  |  | 10531125
30.03 | Heavy Maintenance Facility |  |  |  | 0 |  |  |  | 0
30.04 | Storage or Maintenance of Way Building |  |  |  | 0 |  |  |  | 0
30.05 | Yard and Yard Track |  |  |  | 0 |  |  |  | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 10 | 44350000 | 9000000 | 53350000 | 5335000 | 23.89% | 13.54% | 54167250 | 1.0153
40.01 | Demolition, Clearing, Earthwork |  | 9000000 | 1800000 | 10800000 |  |  |  | 10965441.4246
40.02 | Site Utilities, Utility Relocation |  | 18000000 | 3600000 | 21600000 |  |  |  | 21930882.8491
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  |  |  | 0 |  |  |  | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 9000000 | 1800000 | 10800000 |  |  |  | 10965441.4246
40.05 | Site structures including retaining walls, sound walls |  |  |  | 0 |  |  |  | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 8350000 | 1800000 | 10150000 |  |  |  | 10305484.3018
40.07 | Automobile, bus, van accessways including roads, parking lots |  |  |  | 0 |  |  |  | 0
40.08 | Temporary Facilities and other indirect costs during construction |  |  |  | 0 |  |  |  | 0
50 SYSTEMS |  | 10 | 25000000 | 5000000 | 30000000 | 3000000 | 13.43% | 7.612% | 32149428.75 | 1.0716
50.01 | Train control and signals |  | 9000000 | 1000000 | 10000000 |  |  |  | 10716476.25
50.02 | Traffic signals and crossing protection |  | 2000000 | 500000 | 2500000 |  |  |  | 2679119.0625
50.03 | Traction power supply: substations |  | 4000000 | 1000000 | 5000000 |  |  |  | 5358238.125
50.04 | Traction power distribution: catenary and third rail |  | 4000000 | 1000000 | 5000000 |  |  |  | 5358238.125
50.05 | Communications |  | 4000000 | 1000000 | 5000000 |  |  |  | 5358238.125
50.06 | Fare collection system and equipment |  | 2000000 | 500000 | 2500000 |  |  |  | 2679119.0625
50.07 | Central Control |  |  |  | 0 |  |  |  | 0
Construction Subtotal (10 - 50) |  | 10 | 185350000 | 38000000 | 223350000 | 22335000 | 100% | 56.67% | 233777357.5
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 10 | 30175000 | 5000000 | 35175000 | 3517500 |  | 8.925% | 35350000 | 1.005
60.01 | Purchase or lease of real estate |  | 30175000 | 5000000 | 35175000 |  |  |  | 35350000
60.02 | Relocation of existing households and businesses |  |  |  | 0 |  |  |  | 0
70 VEHICLES (number) |  | 15 | 27000000 | 3000000 | 30000000 | 2000000 |  | 7.612% | 31593375 | 1.0531
70.01 | Light Rail | 15 | 27000000 | 3000000 | 30000000 | 2000000 |  |  | 31593375
70.02 | Heavy Rail |  |  |  | 0 |  |  |  | 0
70.03 | Commuter Rail |  |  |  | 0 |  |  |  | 0
70.04 | Bus |  |  |  | 0 |  |  |  | 0
70.05 | Other |  |  |  | 0 |  |  |  | 0
70.06 | Non-revenue vehicles |  |  |  | 0 |  |  |  | 0
70.07 | Spare parts |  |  |  | 0 |  |  |  | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 10 | 70000000 | 7168000 | 77168000 | 7716800 | 34.55% | 19.58% | 77423560.75 | 1.0033
80.01 | Preliminary Engineering |  | 5000000 | 668000 | 5668000 |  |  |  | 5686770.9715
80.02 | Final Design |  | 20000000 | 2000000 | 22000000 |  |  |  | 22072858.3934
80.03 | Project Management for Design and Construction |  | 5000000 | 500000 | 5500000 |  |  |  | 5518214.5983
80.04 | Construction Administration & Management |  | 20000000 | 2000000 | 22000000 |  |  |  | 22072858.3934
80.05 | Professional Liability and other Non-Construction Insurance |  | 5000000 | 500000 | 5500000 |  |  |  | 5518214.5983
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 5000000 | 500000 | 5500000 |  |  |  | 5518214.5983
80.07 | Surveys, Testing, Investigation, Inspection |  | 5000000 | 500000 | 5500000 |  |  |  | 5518214.5983
80.08 | Start up |  | 5000000 | 500000 | 5500000 |  |  |  | 5518214.5983
Subtotal (10 - 80) |  | 10 | 312525000 | 53168000 | 365693000 | 36569300 |  | 92.79% | 378144293.25
90 UNALLOCATED CONTINGENCY |  |  |  |  | 20000000 |  |  | 5.075% | 21074714.375 | 1.0537
Subtotal (10 - 90) |  | 10 |  |  | 385693000 | 38569300 |  | 97.87% | 399219007.625
100 FINANCE CHARGES |  |  |  |  | 8408031.2088 |  |  | 2.133% | 11000000 | 1.3083
Total Project Cost (10 - 100) |  | 10 |  |  | 394101031.2088 | 39410103.1209 |  | 100% | 410219007.625 | 1.0409
Allocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 17.01%
Unallocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 6.399%
Total Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 23.41%
Unallocated Contingency as % of Subtotal (10 - 80) |  |  |  |  | 5.469%
YOE Construction Cost per Mile (X000) | [8 empty] | 23377735.75
YOE Total Project Cost per Mile Not Including Vehicles (X000) | [8 empty] | 37862563.2625
YOE Total Project Cost per Mile (X000) | [8 empty] | 41021900.7625
Note on D8: For all cells, enter costs to the $1. Note, all costs will be displayed to the nearest $1,000!
Note on F76: Enter finance charges on Inflation Worksheet.
Note on I19: Preparing for bid: For each separate contract package generate a Main Worksheet and an Inflation Worksheet. In the Special Conditions of the Contract, require the construction contractor to update these worksheets and submit them with the monthly pay application. This should make it easy to track costs in the SCC format throughout construction, and make it easy to submit the final costs to FTA at contract closeout and at the two-year post-rev ops date required by the Before and After Study.
Note on J3: Year of Base Year Dollars should match the year in "Today's Date."
Note on J6: YOE Dollars automatically arrive from Inflation Worksheet.
Note on J8: YOE costs for individual line items within a Category are derived as a percentage of the YOE cost of the Category.

## Inflation
I N F L A T I O N W O R K S H E E T | [5 empty] | (Rev.14, August 5, 2011)
Insert Project Sponsor's Name here |  |  |  |  | Today's Date | 2011-08-05
Insert Project Name and Location |  |  |  |  | Yr of Base Year $ | 2011
Insert Current Phase (e.g. Applic.for PE, PE, FD, Applic. for FFGA, Construction, Rev Ops) |  |  |  |  | Yr of Revenue Ops | 2020
Insert comments, notes, etc.
BASE YEAR DOLLARS (X$000) | Base Yr Dollars | Double-Check Total | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 100000000 | 100000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 45000000 | 45000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 53350000 | 53350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350000 | 20000000 | 13000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 35175000 | 35175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5175000 | 20000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77168000 | 77167534.0284 | 0 | 0 | 0 | 0 | 0 | 0 | 593843.1528 | 1147523.0006 | 1108717.875 | 2142450 | 5175000 | 50000000 | 10000000 | 5000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 20000000 | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 8408031.2088 | 8408031.2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535612.5 | 517500 | 500000 | 483091.7874 | 466755.3502 | 450971.3528 | 435721.1138 | 420986.5834 | 406750.3222 | 392995.4803 | 379705.7781 | 366865.4861 | 354459.4069 | 342472.8569 | 330891.6491 | 319702.0765 | 308890.8951 | 298445.3093 | 288352.9559 | 278601.8897 | 269180.5698 | 260077.8452
Total Project Cost (10 - 100) | 394101031.2088 | 394100565.2372 | 0 | 0 | 0 | 0 | 0 | 0 | 593843.1528 | 1147523.0006 | 1108717.875 | 2678062.5 | 21217500 | 105500000 | 123483091.7874 | 105466755.3502 | 27450971.3528 | 435721.1138 | 420986.5834 | 406750.3222 | 392995.4803 | 379705.7781 | 366865.4861 | 354459.4069 | 342472.8569 | 330891.6491 | 319702.0765 | 308890.8951 | 298445.3093 | 288352.9559 | 278601.8897 | 269180.5698 | 260077.8452
Inflation Rate |  |  | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035
Compounded Inflation Factor |  |  | 1.46 | 1.4106 | 1.3629 | 1.3168 | 1.2723 | 1.2293 | 1.1877 | 1.1475 | 1.1087 | 1.0712 | 1.035 | 1 | 1.035 | 1.0712 | 1.1087 | 1.1475 | 1.1877 | 1.2293 | 1.2723 | 1.3168 | 1.3629 | 1.4106 | 1.46 | 1.5111 | 1.564 | 1.6187 | 1.6753 | 1.734 | 1.7947 | 1.8575 | 1.9225
YEAR OF EXPENDITURE DOLLARS (X$000) | YOE Dollars |  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 104780125 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 46575000 | 48205125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 32149428.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350000 | 10712250 | 11087178.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10531125 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5175000 | 5356125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 54167250 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10000000 | 20000000 | 13455000 | 10712250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 32149428.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350000 | 10712250 | 11087178.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 35350000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 20000000 | 10350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 31593375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15525000 | 16068375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77423560.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 2000000 | 5000000 | 50000000 | 10350000 | 5356125 | 2217435.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 21074714.375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5175000 | 5356125 | 5543589.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 11000000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
Total Project Cost (10 - 100) | 410219007.625 |  | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 2500000 | 20500000 | 105500000 | 127805000 | 112978625 | 30435382.625 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
Note on E20: In Row 20 for each year insert the rate of inflation that you believe to be correct. Numbers shown are for example only.
Note on E24: For past years, enter the actual dollars spent in each year. The dollars will inflate when converted to the current base year.
Note on E33: Enter Finance Charges on this line.
Note on L8: Because of inflation, it costs more to buy the same goods and services today than it would have cost in previous years. The total base year dollar cost is a concept that represents the total project cost if the project were planned, designed and built in only one year, the designated base year.
Note on P8: In the white cells, insert project costs in the year in which they occurred (lower rows) or are planned to occur (upper rows) through the completion of the project or the fulfillment of the New Starts funding commitment, whichever is expected to occur later in time.
Note on P21: In the Base Year no inflation multiplier is used.

## Project Description
P R O J E C T D E S C R I P T I O N - B U I L D A L T E R N A T I V E |  |  | (Rev.14, August 5, 2011)
Insert Project Sponsor's Name here |  | Today's Date | 2011-08-05
Insert Project Name and Location
Insert Current Phase (e.g. Applic.for PE, PE, FD, Applic. for FFGA, Construction, Rev Ops)
Describe the project elements to explain the unit costs shown on the Main Worksheet. Example: A 20-mile new light rail project has its guideway entirely on grade except for a one-eighth mile bridge over a river. The bridge or aerial structure may have a relatively high unit cost because there is little economy of scale. Mention precedents and reference points used in the development of costs for this project. Mention other aspects of this project that were important considerations in estimating costs. These could include the physical context, site constraints; design parameters; institutional, contracting and procurement conditions; project schedule, etc.
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
80.01 | Preliminary Engineering
80.02 | Final Design
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Professional Liability and other Non-Construction Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY
Subtotal (10 - 90)
100 FINANCE CHARGES
Total Project Cost (10 - 100)
Note on C8: These rows can be expanded to fit your narrative. Delete lines that are not needed.
Note on C27: For each garage, list station name, number of floors above and below grade, and number of spaces in each garage
Note on C42: For each parking lot, list station name and number of spaces

## Schedule
S C H E D U L E |  |  | (Rev.14, August 5, 2011)
Insert Project Sponsor's Name here | Today's Date |  | 2011-08-05
Insert Project Name and Location | Yr of Base Year $ |  | 2011
Insert Current Phase (e.g. Applic.for PE, PE, FD, Applic. for FFGA, Construction, Rev Ops) | Yr of Revenue Ops |  | 2020
Insert comments, notes, etc. |  | Start Date | End Date | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Preliminary Engineering |  | 2004-01-01 | 2009-01-01
Design
Develop cost estimate, schedule, ridership forecast
Conduct reviews
Develop FEIS, receive Record of Decision
Submit request / receive FTA approval to enter Final Design
Final Design |  | 2009-01-01 | 2011-01-01
Develop the contract documents for the Build Alternative
Develop cost estimate, schedule
Acquire real estate; relocate households and businesses
Conduct reviews
Submit request / receive FTA approval for FFGA
Issue requests for bids, make awards of construction contracts
Construction |  | 2011-01-01 | 2013-01-01
Construct fixed infrastructure
Insert Contract Package Number and Description (i.e. Guideway, Stations, Systems, etc.)
Insert Contract Package Number and Description (i.e. Guideway, Stations, Systems, etc.)
Finalize real estate acquisitions and relocations
Acquire and test vehicles
Revenue Ops / Closeout of Project |  | 2013-01-01 | 2015-03-01
Revenue Operations
Before and After Study: Two years post Rev Ops
Fulfillment of the New Starts funding commitment
Completion of project close-out, resolution of claims
Note on C7: On this Schedule and on the Inflation Worksheet, indicate the start of PE with the date of FTA's letter approving the project into PE.
Note on E6: Delete years not required.

## BUILD Annualized
A N N U A L I Z E D C O S T - B U I L D A L T E R N A T I V E | [8 empty] | (Rev.14, August 5, 2011)
Insert Project Sponsor's Name here | [6 empty] | Today's Date |  | 2011-08-05
Insert Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2011
Insert Current Phase (e.g. Applic.for PE, PE, FD, Applic. for FFGA, Construction, Rev Ops) | [6 empty] | Yr of Revenue Ops |  | 2020
|  | Quantity | Total Base Year Dollars (X000) | Cat. 80 Prof. Svc. spread proportionally over Cats. 10 - 50 (X000) | Spread Cat. 90 Unalloc. Cont. according to perceived risks (X000) | Revised Total Base Year Dollars (X000) | Years of Useful Life | Annualization Factor (based on 7% rate) [.07/1 - (1.07)^-no. yrs] | Annualized Cost (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 10 | 100000000 | 34550257.4435 | 7000000 | 141550257.4435 |  |  | 9910622.4231
10.01 | Guideway: At-grade exclusive right-of-way | 10 | 100000000 | 34550257.4435 | 7000000 | 141550257.4435 | 125 | 0.070015 | 9910622.4231
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.09 | Track: Direct fixation |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.1 | Track: Embedded |  | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.11 | Track: Ballasted |  | 0 | 0 |  | 0 | 35 | 0.077234 | 0
10.12 | Track: Special (switches, turnouts) |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.13 | Track: Vibration and noise dampening |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 20 | 30000000 | 10365077.233 | 10000000 | 50365077.233 |  |  | 3556757.9408
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 20 | 30000000 | 10365077.233 | 10000000 | 50365077.233 | 70 | 0.07062 | 3556757.9408
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.05 | Joint development |  | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.06 | Automobile parking multi-story structure |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
20.07 | Elevators, escalators |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 10000000 | 3455025.7443 | 0 | 13455025.7443 |  |  | 974949.141
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.02 | Light Maintenance Facility |  | 10000000 | 3455025.7443 |  | 13455025.7443 | 50 | 0.07246 | 974949.141
30.03 | Heavy Maintenance Facility |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.04 | Storage or Maintenance of Way Building |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.05 | Yard and Yard Track |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 53350000 | 18432562.3461 | 500000 | 72282562.3461 |  |  | 5405970.527
40.01 | Demolition, Clearing, Earthwork |  | 10800000 | 3731427.8039 |  | 14531427.8039 | 125 | 0.070015 | 1017415.9824
40.02 | Site Utilities, Utility Relocation |  | 21600000 | 7462855.6078 |  | 29062855.6078 | 125 | 0.070015 | 2034831.9648
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 0 | 0 |  | 0 | 125 | 0.070015 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 10800000 | 3731427.8039 |  | 14531427.8039 | 125 | 0.070015 | 1017415.9824
40.05 | Site structures including retaining walls, sound walls |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 10150000 | 3506851.1305 | 500000 | 14156851.1305 | 20 | 0.094393 | 1336306.5975
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 0 | 0 |  | 0 | 20 | 0.094393 | 0
40.08 | Temporary Facilities and other indirect costs during construction |  | 0 | 0 |  | 0 | 100 | 0.070081 | 0
50 SYSTEMS |  |  | 30000000 | 10365077.233 | 500000 | 40865077.233 |  |  | 3348954.3091
50.01 | Train control and signals |  | 10000000 | 3455025.7443 | 500000 | 13955025.7443 | 30 | 0.080586 | 1124585.3356
50.02 | Traffic signals and crossing protection |  | 2500000 | 863756.4361 |  | 3363756.4361 | 30 | 0.080586 | 271073.0335
50.03 | Traction power supply: substations |  | 5000000 | 1727512.8722 |  | 6727512.8722 | 50 | 0.07246 | 487474.5705
50.04 | Traction power distribution: catenary and third rail |  | 5000000 | 1727512.8722 |  | 6727512.8722 | 30 | 0.080586 | 542146.0669
50.05 | Communications |  | 5000000 | 1727512.8722 |  | 6727512.8722 | 20 | 0.094393 | 635029.623
50.06 | Fare collection system and equipment |  | 2500000 | 863756.4361 |  | 3363756.4361 | 25 | 0.085811 | 288645.6796
50.07 | Central Control |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
Construction Subtotal (10 - 50) |  |  | 223350000 | 77168000 | 18000000 | 318518000 |  |  | 23197254.3411
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 35175000 |  | 1000000 | 36175000 |  |  | 2532787.8072
60.01 | Purchase or lease of real estate |  | 35175000 |  | 1000000 | 36175000 | 125 | 0.070015 | 2532787.8072
60.02 | Relocation of existing households and businesses |  | 0 |  |  | 0 | 125 | 0.070015 | 0
70 VEHICLES (number) |  | 15 | 30000000 |  | 1000000 | 31000000 |  |  | 2660126.0338
70.01 | Light Rail | 15 | 30000000 |  | 1000000 | 31000000 | 25 | 0.085811 | 2660126.0338
70.02 | Heavy Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.03 | Commuter Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.04 | Bus | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.05 | Other | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.06 | Non-revenue vehicles | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.07 | Spare parts | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  |  | 77168000
80.01 | Preliminary Engineering |  | 5668000
80.02 | Final Design |  | 22000000
80.03 | Project Management for Design and Construction |  | 5500000
80.04 | Construction Administration & Management |  | 22000000
80.05 | Professional Liability and other Non-Construction Insurance |  | 5500000
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 5500000
80.07 | Surveys, Testing, Investigation, Inspection |  | 5500000
80.08 | Start up |  | 5500000
Subtotal (10 - 80) |  |  | 365693000
90 UNALLOCATED CONTINGENCY |  |  | 20000000
Subtotal (10 - 90) |  |  | 385693000 | 77168000 | 20000000 | 385693000 |  |  | 28390168.1821
XX.XX | Insert here other components req'd in Annualized Cost |  | 0 |  | 0 | 0 | 125 | 0.070015 | 0
XX.XX | Insert here other components req'd in Annualized Cost |  | 0 |  | 0 | 0 | 125 | 0.070015 | 0
XX.XX | Insert here other components req'd in Annualized Cost |  | 0 |  | 0 | 0 | 125 | 0.070015 | 0
XX.XX | Insert here other components req'd in Annualized Cost |  | 2000 |  | 0 | 2000 | 125 | 0.070015 | 140.0297
TOTAL |  |  | 385695000 |  | 20000000 | 385695000 |  |  | 28390308.2118
Note on B79: Additional project components may be required to be included in the Annualized Cost. Insert vehicle additions in Cat. 70. Insert any other item in Rows 76 - 79; insert useful life and annualization factor as well.
Note on E75: E75 and F75 are double-checks
Note on H60: The range for buses is 12 to 18 years. Provide supporting documentation for an estimated useful life of more than 12 years.

## Fund Source by Cat
F U N D I N G S O U R C E S B Y C A T E G O R Y | [11 empty] | (Rev.14, August 5, 2011)
Insert Project Sponsor's Name here | [9 empty] | Today's Date |  | 2011-08-05
Insert Project Name and Location
Insert Current Phase (e.g. Applic.for PE, PE, FD, Applic. for FFGA, Construction, Rev Ops)
| Cost |  | Funding Summary |  |  | 50% | 50% | 71% | 29%
| YOE Cost (X000) | Double- check Total | Federal 5309 New Starts Funds | Federal Other Funds | Local Funds
[6 empty] | Federal 5309 New Starts | Local | Federal Other | Local | Federal Other | Local | Federal Other | Local
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 104780125 | 104780000 | 50000000 | 4780000 | 50000000 | 50000000 | 50000000 | 4780000
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 32149428.75 | 32149000 | 25000000 | 2149000 | 5000000 | 25000000 | 5000000 | 2149000
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10531125 | 10531000 | 5000000 | 531000 | 5000000 | 5000000 | 5000000 | 531000
40 SITEWORK & SPECIAL CONDITIONS | 54167250 | 51062000 | 20000000 | 11062000 | 20000000 | 20000000 | 20000000 | 11062000
50 SYSTEMS | 32149428.75 | 32149000 | 15000000 | 2149000 | 15000000 | 15000000 | 15000000 | 2149000
60 ROW, LAND, EXISTING IMPROVEMENTS | 35350000 | 35350000 | 15000000 | 350000 | 20000000 | 15000000 | 20000000 | 350000
70 VEHICLES (number) | 31593375 | 31593000 | 15000000 | 1593000 | 15000000 | 15000000 | 15000000 | 1593000
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77423560.75 | 77424000 | 50000000 | 2424000 | 25000000 | 50000000 | 25000000 | 2424000
90 UNALLOCATED CONTINGENCY | 21074714.375 | 21075000 | 10000000 | 1075000 | 10000000 | 10000000 | 10000000 | 1075000
100 FINANCE CHARGES | 11000000 | 14106000 | 5000000 | 4106000 | 5000000 | 5000000 | 5000000 | 4106000
Total Project Cost (10 - 100) | 410219007.625 | 410219000 | 210000000 | 30219000 | 170000000 | 210000000 | 170000000 | 30219000 | 0 | 0 | 0 | 0 | 0
Percentage of Total Project Cost | 100% |  | 51.19% | 7.367% | 41.44% | 51.19% | 41.44% | 7.367% | 0% | 0% | 0% | 0% | 0%
|  |  | 51.19% | 48.81%
100%
Note on H6: Indicate pairs or groups of funds, percentage match etc.
Note on O8: Insert additional columns as required.

## Fund Source by Year
F U N D I N G S O U R C E S B Y Y E A R | [6 empty] | (Rev.14, August 5, 2011)
Insert Project Sponsor's Name here |  |  |  |  | Today's Date |  | 2011-08-05
Insert Project Name and Location
Insert Current Phase (e.g. Applic.for PE, PE, FD, Applic. for FFGA, Construction, Rev Ops)
|  |  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2030
Total Project Cost In YOE Dollars Below insert funding sources and amounts for each year. | 403719007.625 | double check | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 2500000 | 20500000 | 105500000 | 127805000 | 112978625 | 30435382.625 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
Federal 5309 New Starts | 210000000 | 210000000 | 2010: 2000000; 2011: 8000000; 2012: 100000000; 2013: 100000000
Local | 170000000 | 170000000 | 2000: 0; 2001: 0; 2002: 0; 2003: 0; 2004: 2000000; 2005: 2000000; 2007: 2000000; 2008: 2000000; 2009: 2000000; 2010: 2000000; 2011: 2000000; 2012: 90000000; 2013: 66000000
Federal Other | 30219000 | 30219000 | 2010: 4000000; 2011: 4000000; 2012: 10000000; 2013: 12219000
Total Project Cost (10 - 100) | 410219000 | 410219000 | 0 | 0 | 0 | 0 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 8000000 | 14000000 | 200000000 | 178219000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## BASELINE Main
M A I N W O R K S H E E T - B A S E L I N E A L T E R N A T I V E | [8 empty] | (Rev.14, August 5, 2011)
Insert Project Sponsor's Name here | [6 empty] | Today's Date |  | 2011-08-05
Insert Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2011
Insert Current Phase (e.g. Applic.for PE, PE, FD, Applic. for FFGA, Construction, Rev Ops) | [6 empty] | Yr of Revenue Ops |  | 2020
|  | Quantity | Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Base Year Dollars Unit Cost (X000) | Base Year Dollars Percentage of Construction Cost | Base Year Dollars Percentage of Total Project Cost | Baseline Alternative Cost Parameters (X000) see New Starts Reporting Instructions for additional info
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 10 | 10000000 | 1000000 | 11000000 | 1100000 | 29.89% | 17.24%
10.01 | Guideway: At-grade exclusive right-of-way |  |  |  | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 10 | 10000000 | 1000000 | 11000000 | 1100000 |  |  | 1273/route mile
10.03 | Guideway: At-grade in mixed traffic |  |  |  | 0
10.04 | Guideway: Aerial structure |  |  |  | 0
10.05 | Guideway: Built-up fill |  |  |  | 0
10.06 | Guideway: Underground cut & cover |  |  |  | 0
10.07 | Guideway: Underground tunnel |  |  |  | 0
10.08 | Guideway: Retained cut or fill |  |  |  | 0
10.09 | Track: Direct fixation |  |  |  | 0
10.1 | Track: Embedded |  |  |  | 0
10.11 | Track: Ballasted |  |  |  | 0
10.12 | Track: Special (switches, turnouts) |  |  |  | 0
10.13 | Track: Vibration and noise dampening |  |  |  | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 36 | 7000000 | 1000000 | 8000000 | 222222.2222 | 21.74% | 12.54%
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 36 | 7000000 | 1000000 | 8000000 | 222222.2222 |  |  | 238/station
20.02 | Aerial station, stop, shelter, mall, terminal, platform |  |  |  | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform |  |  |  | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. |  |  |  | 0
20.05 | Joint development |  |  |  | 0
20.06 | Automobile parking multi-story structure |  |  |  | 0
20.07 | Elevators, escalators |  |  |  | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 10 | 4000000 | 1000000 | 5000000 | 500000 | 13.59% | 7.837%
30.01 | Administration Building: Office, sales, storage, revenue counting |  |  |  | 0
30.02 | Light Maintenance Facility |  | 4000000 | 1000000 | 5000000
30.03 | Heavy Maintenance Facility |  |  |  | 0
30.04 | Storage or Maintenance of Way Building |  |  |  | 0
30.05 | Yard and Yard Track |  |  |  | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 10 | 8300000 | 1800000 | 10100000 | 1010000 | 27.45% | 15.83%
40.01 | Demolition, Clearing, Earthwork |  | 5000000 | 100000 | 5100000
40.02 | Site Utilities, Utility Relocation |  | 1000000 | 500000 | 1500000
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  |  |  | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 1000000 | 200000 | 1200000
40.05 | Site structures including retaining walls, sound walls |  |  |  | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 1000000 | 1000000 | 2000000
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 200000 |  | 200000 |  |  |  | 6/on-grade space
40.08 | Temporary Facilities and other indirect costs during construction |  | 100000 |  | 100000
50 SYSTEMS |  | 10 | 2305000 | 392000 | 2697000 | 269700 | 7.329% | 4.227%
50.01 | Train control and signals |  |  |  | 0
50.02 | Traffic signals and crossing protection |  | 1125000 | 200000 | 1325000 |  |  |  | 30/intersection
50.03 | Traction power supply: substations |  |  |  | 0
50.04 | Traction power distribution: catenary and third rail |  |  |  | 0
50.05 | Communications |  | 600000 | 72000 | 672000 |  |  |  | 14.4/bus and 14.4/sign
50.06 | Fare collection system and equipment |  | 180000 | 20000 | 200000 |  |  |  | 11.8/bus
50.07 | Central Control |  | 400000 | 100000 | 500000 |  |  |  | 18 - 30/bus
Construction Subtotal (10 - 50) |  | 10 | 31605000 | 5192000 | 36797000 | 3679700 | 100% | 57.68%
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 10 | 1000000 | 200000 | 1200000 | 120000 |  | 1.881%
60.01 | Purchase or lease of real estate |  | 1000000 | 200000 | 1200000
60.02 | Relocation of existing households and businesses |  |  |  | 0
70 VEHICLES (number) |  | 20 | 10000000 | 3000000 | 13000000 | 650000 |  | 20.38%
70.01 | Light Rail |  |  |  | 0
70.02 | Heavy Rail |  |  |  | 0
70.03 | Commuter Rail |  |  |  | 0
70.04 | Bus | 20 | 10000000 | 3000000 | 13000000 | 650000 |  |  | 530 conventional 798 articulated 1060 hybrid
70.05 | Other |  |  |  | 0
70.06 | Non-revenue vehicles |  |  |  | 0
70.07 | Spare parts |  |  |  | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 10 | 9800000 | 0 | 9800000 | 980000 | 26.63% | 15.36% | 25-35% of Construction 10-50
80.01 | Preliminary Engineering |  | 2000000 |  | 2000000
80.02 | Final Design |  | 3500000 |  | 3500000
80.03 | Project Management for Design and Construction |  | 2000000 |  | 2000000
80.04 | Construction Administration & Management |  | 1500000 |  | 1500000
80.05 | Professional Liability and other Non-Construction Insurance |  | 500000 |  | 500000
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  |  |  | 0
80.07 | Surveys, Testing, Investigation, Inspection |  | 150000 |  | 150000
80.08 | Start up |  | 150000 |  | 150000
Subtotal (10 - 80) |  | 10 | 52405000 | 8392000 | 60797000 | 6079700 |  | 95.3%
90 UNALLOCATED CONTINGENCY |  |  |  |  | 3000000 |  |  | 4.702%
Subtotal (10 - 90) |  | 10 |  |  | 63797000 | 6379700 |  | 100%
100 FINANCE CHARGES |  |  |  |  | NA
Total Project Cost (10 - 100) |  | 10 |  |  | 63797000 | 6379700 |  | 100%
Total Base Year Cost per Mile Not Including Vehicles (X000) | [5 empty] | 5079700
Allocated Contingency as % of Base Yr Dollars w/o Cont. |  |  |  |  | 16.01%
Unallocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 5.725%
Total Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 21.74%
Unallocated Contingency as % of Subtotal (10 - 80) |  |  |  |  | 4.934%
Note on J9: August 2011: The cost parameters have been increased by 3% from the 2010 costs. They include allocated contingency as before.

## BASELINE Annualized
A N N U A L I Z E D C O S T - B A S E L I N E A L T E R N A T I V E | [8 empty] | (Rev.14, August 5, 2011)
Insert Project Sponsor's Name here | [6 empty] | Today's Date |  | 2011-08-05
Insert Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2011
Insert Current Phase (e.g. Applic.for PE, PE, FD, Applic. for FFGA, Construction, Rev Ops) | [6 empty] | Yr of Revenue Ops |  | 2020
|  | Quantity | Total Base Year Dollars (X000) | Cat. 80 Prof. Svc. spread proportionally over Cats. 10 - 50 (X000) | Spread Cat. 90 Unalloc. Cont. according to perceived risks (X000) | Revised Total Base Year Dollars (X000) | Years of Useful Life | Annualization Factor (based on 7% rate) [.07/1 - (1.07)^-no. yrs] | Annualized Cost (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 10 | 11000000 | 2929586.6511 | 1000000 | 14929586.6511 |  |  | 1203121.6941
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | 0 | 0 | 0 | 125 | 0.070015 | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 10 | 11000000 | 2929586.6511 | 1000000 | 14929586.6511 | 30 | 0.080586 | 1203121.6941
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.09 | Track: Direct fixation |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.1 | Track: Embedded |  | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.11 | Track: Ballasted |  | 0 | 0 |  | 0 | 35 | 0.077234 | 0
10.12 | Track: Special (switches, turnouts) |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.13 | Track: Vibration and noise dampening |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 36 | 8000000 | 2130608.4735 | 1000000 | 11130608.4735 |  |  | 786038.3077
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 36 | 8000000 | 2130608.4735 | 1000000 | 11130608.4735 | 70 | 0.07062 | 786038.3077
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.05 | Joint development |  | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.06 | Automobile parking multi-story structure |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
20.07 | Elevators, escalators |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 5000000 | 1331630.2959 | 200000 | 6531630.2959 |  |  | 473280.9485
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.02 | Light Maintenance Facility |  | 5000000 | 1331630.2959 | 200000 | 6531630.2959 | 50 | 0.07246 | 473280.9485
30.03 | Heavy Maintenance Facility |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.04 | Storage or Maintenance of Way Building |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.05 | Yard and Yard Track |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 10100000 | 2689893.1978 | 200000 | 12989893.1978 |  |  | 977409.2439
40.01 | Demolition, Clearing, Earthwork |  | 5100000 | 1358262.9019 | 200000 | 6658262.9019 | 125 | 0.070015 | 466177.3903
40.02 | Site Utilities, Utility Relocation |  | 1500000 | 399489.0888 |  | 1899489.0888 | 125 | 0.070015 | 132992.4756
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 0 | 0 |  | 0 | 125 | 0.070015 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 1200000 | 319591.271 |  | 1519591.271 | 125 | 0.070015 | 106393.9805
40.05 | Site structures including retaining walls, sound walls |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 2000000 | 532652.1184 |  | 2532652.1184 | 20 | 0.094393 | 239064.4433
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 200000 | 53265.2118 |  | 253265.2118 | 20 | 0.094393 | 23906.4443
40.08 | Temporary Facilities and other indirect costs during construction |  | 100000 | 26632.6059 |  | 126632.6059 | 100 | 0.070081 | 8874.5098
50 SYSTEMS |  |  | 2697000 | 718281.3816 | 0 | 3415281.3816 |  |  | 288297.2814
50.01 | Train control and signals |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
50.02 | Traffic signals and crossing protection |  | 1325000 | 352882.0284 |  | 1677882.0284 | 30 | 0.080586 | 135214.4782
50.03 | Traction power supply: substations |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
50.04 | Traction power distribution: catenary and third rail |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
50.05 | Communications |  | 672000 | 178971.1118 |  | 850971.1118 | 20 | 0.094393 | 80325.653
50.06 | Fare collection system and equipment |  | 200000 | 53265.2118 |  | 253265.2118 | 25 | 0.085811 | 21732.8188
50.07 | Central Control |  | 500000 | 133163.0296 |  | 633163.0296 | 30 | 0.080586 | 51024.3314
Construction Subtotal (10 - 50) |  |  | 36797000 | 9800000 | 2400000 | 48997000 |  |  | 3728147.4755
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 1200000 |  | 0 | 1200000 |  |  | 84017.8402
60.01 | Purchase or lease of real estate |  | 1200000 |  |  | 1200000 | 125 | 0.070015 | 84017.8402
60.02 | Relocation of existing households and businesses |  | 0 |  |  | 0 | 125 | 0.070015 | 0
70 VEHICLES (number) |  | 20 | 13000000 |  | 600000 | 13600000 |  |  | 1712267.0457
70.01 | Light Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.02 | Heavy Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.03 | Commuter Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.04 | Bus | 20 | 13000000 |  | 600000 | 13600000 | 12 | 0.1259 | 1712267.0457
70.05 | Other | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.06 | Non-revenue vehicles | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.07 | Spare parts | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  |  | 9800000
80.01 | Preliminary Engineering |  | 2000000
80.02 | Final Design |  | 3500000
80.03 | Project Management for Design and Construction |  | 2000000
80.04 | Construction Administration & Management |  | 1500000
80.05 | Professional Liability and other Non-Construction Insurance |  | 500000
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 0
80.07 | Surveys, Testing, Investigation, Inspection |  | 150000
80.08 | Start up |  | 150000
Subtotal (10 - 80) |  |  | 60797000
90 UNALLOCATED CONTINGENCY |  |  | 3000000
Subtotal (10 - 90) |  |  | 63797000 | 9800000 | 3000000 | 63797000 |  |  | 5524432.3614
Note on E75: E75 and F75 are double-checks.
Note on H60: The range for buses is 12 to 18 years. Provide supporting documentation for an estimated useful life of more than 12 years.

## FFGA A3T1
Table 1 - BCE by Standard Cost Category
Applicable Line Items Only |  | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 104780125
10.01 | Guideway: At-grade exclusive right-of-way | 104780125
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0
10.03 | Guideway: At-grade in mixed traffic | 0
10.04 | Guideway: Aerial structure | 0
10.05 | Guideway: Built-up fill | 0
10.06 | Guideway: Underground cut & cover | 0
10.07 | Guideway: Underground tunnel | 0
10.08 | Guideway: Retained cut or fill | 0
10.09 | Track: Direct fixation | 0
10.1 | Track: Embedded | 0
10.11 | Track: Ballasted | 0
10.12 | Track: Special (switches, turnouts) | 0
10.13 | Track: Vibration and noise dampening | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 32149428.75
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 32149428.75
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0
20.05 | Joint development | 0
20.06 | Automobile parking multi-story structure | 0
20.07 | Elevators, escalators | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 10531125
30.01 | Administration Building: Office, sales, storage, revenue counting | 0
30.02 | Light Maintenance Facility | 10531125
30.03 | Heavy Maintenance Facility | 0
30.04 | Storage or Maintenance of Way Building | 0
30.05 | Yard and Yard Track | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 54167250
40.01 | Demolition, Clearing, Earthwork | 10965441.4246
40.02 | Site Utilities, Utility Relocation | 21930882.8491
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 10965441.4246
40.05 | Site structures including retaining walls, sound walls | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 10305484.3018
40.07 | Automobile, bus, van accessways including roads, parking lots | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0
50 SYSTEMS |  | 32149428.75
50.01 | Train control and signals | 10716476.25
50.02 | Traffic signals and crossing protection | 2679119.0625
50.03 | Traction power supply: substations | 5358238.125
50.04 | Traction power distribution: catenary and third rail | 5358238.125
50.05 | Communications | 5358238.125
50.06 | Fare collection system and equipment | 2679119.0625
50.07 | Central Control | 0
Construction Subtotal (10 - 50) |  | 233777357.5
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 35350000
60.01 | Purchase or lease of real estate | 35350000
60.02 | Relocation of existing households and businesses | 0
70 VEHICLES (number) |  | 31593375
70.01 | Light Rail | 31593375
70.02 | Heavy Rail | 0
70.03 | Commuter Rail | 0
70.04 | Bus | 0
70.05 | Other | 0
70.06 | Non-revenue vehicles | 0
70.07 | Spare parts | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  | 77423560.75
80.01 | Preliminary Engineering | 5686770.9715
80.02 | Final Design | 22072858.3934
80.03 | Project Management for Design and Construction | 5518214.5983
80.04 | Construction Administration & Management | 22072858.3934
80.05 | Professional Liability and other Non-Construction Insurance | 5518214.5983
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 5518214.5983
80.07 | Surveys, Testing, Investigation, Inspection | 5518214.5983
80.08 | Start up | 5518214.5983
Subtotal (10 - 80) |  | 378144293.25
90 UNALLOCATED CONTINGENCY |  | 21074714.375
Subtotal (10 - 90) |  | 399219007.625
100 FINANCE CHARGES |  | 11000000
Total Project Cost (10 - 100) |  | 410219007.625
Note on B1: This sheet, FFGA A3T1, and the sheets that follow become Attachments to the FFGA

## FFGA A3T2
Table 2 - Inflated Cost to Year of Expenditure
| Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Inflation Factor | YOE Dollars TOTAL (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 80000000 | 20000000 | 100000000 | 1.0478 | 104780125
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 28000000 | 2000000 | 30000000 | 1.0716 | 32149428.75
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 8000000 | 2000000 | 10000000 | 1.0531 | 10531125
40 SITEWORK & SPECIAL CONDITIONS | 44350000 | 9000000 | 53350000 | 1.0153 | 54167250
50 SYSTEMS | 25000000 | 5000000 | 30000000 | 1.0716 | 32149428.75
60 ROW, LAND, EXISTING IMPROVEMENTS | 30175000 | 5000000 | 35175000 | 1.005 | 35350000
70 VEHICLES (number) | 27000000 | 3000000 | 30000000 | 1.0531 | 31593375
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 70000000 | 7168000 | 77168000 | 1.0033 | 77423560.75
90 UNALLOCATED CONTINGENCY |  |  | 20000000 | 1.0537 | 21074714.375
100 FINANCE CHARGES |  |  | 8408031.2088 | 1.3083 | 11000000
Total Project Cost (10 - 100) |  |  | 394101031.2088 | 1.0409 | 410219007.625

## A3T3
Table 3 - BCE by Source of Funding
| Total Project Cost in YOE Dollars (X000) | Double Check Total (X000) | Federal 5309 New Starts | Federal Other | Local
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 104780125 | 104780000 | 50000000 | 4780000 | 50000000
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 32149428.75 | 32149000 | 25000000 | 2149000 | 5000000
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10531125 | 10531000 | 5000000 | 531000 | 5000000
40 SITEWORK & SPECIAL CONDITIONS | 54167250 | 51062000 | 20000000 | 11062000 | 20000000
50 SYSTEMS | 32149428.75 | 32149000 | 15000000 | 2149000 | 15000000
60 ROW, LAND, EXISTING IMPROVEMENTS | 35350000 | 35350000 | 15000000 | 350000 | 20000000
70 VEHICLES (number) | 31593375 | 31593000 | 15000000 | 1593000 | 15000000
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77423560.75 | 77424000 | 50000000 | 2424000 | 25000000
90 UNALLOCATED CONTINGENCY | 21074714.375 | 21075000 | 10000000 | 1075000 | 10000000
100 FINANCE CHARGES | 11000000 | 14106000 | 5000000 | 4106000 | 5000000
Total Project Cost (10 - 100) | 410219007.625 | 410219000 | 210000000 | 30219000 | 170000000
Sources of Federal Funding and Matching Share Ratios
| Costs Attributed to Source of Funds (X000) | Federal/ Local Matching Ratio within Source | All Federal Funds (X000) | Local Funds (X000)
Federal 5309 New Starts | 372602000 | 50/50 | 185568000 | 187034000
Federal Other (pls say what..) | 140000000 | 71/29 | 100000000 | 40000000
Total | 512602000 |  | 285568000 | 227034000
Overall Federal Share of Project |  |  | 55.71%
New Starts Share of Project |  |  | 51.19%
Note on A19: Add rows are needed to show all federal funding.
Note on F2: Add columns as required to show all federal funding.

## A3A
Scope and Activity Description
Scope Code | ALI Code | Scope and Activity Line Item Descriptions | Qty |  | Federal 5309 New Starts |  |  | Federal Other |  |  | Project Totals |  |  | Check Total Project Cost in YOE Dollars (X000)
|  |  |  | Total Federal % | Federal | Local | Total | Federal | Local | Total | Federal | Local | Total
14010 | 140110 | GUIDEWAY & TRACK ELEMENTS | 10 | 80.12% | 759000 | 25000000 | 25759000 | 100000000 | 0 | 100000000 | 100759000 | 25000000 | 125759000 | 104780125
14020 | 140220 | STATIONS, STOPS, TERMINALS, INTERMODAL | 20 | 31% | 30000000 | 26781000 | 56781000 | 0 | 40000000 | 40000000 | 30000000 | 66781000 | 96781000 | 32149428.75
14030 | 140330 | SUPPORT FACILITIES, YARDS, SHOPS, ADMIN. BLDGS. |  | 50.51% | 7000000 | 6859000 | 13859000 | 0 | 0 | 0 | 7000000 | 6859000 | 13859000 | 10531125
14040 | 140440 | SITEWORK & SPECIAL CONDITIONS |  | 57.83% | 15000000 | 10938000 | 25938000 | 0 | 0 | 0 | 15000000 | 10938000 | 25938000 | 54167250
14050 | 140550 | SYSTEMS |  | 53.66% | 18000000 | 15543000 | 33543000 | 0 | 0 | 0 | 18000000 | 15543000 | 33543000 | 32149428.75
14060 | 140660 | ROW, LAND, EXISTING IMPROVEMENTS |  | 42.41% | 10000000 | 13582000 | 23582000 | 0 | 0 | 0 | 10000000 | 13582000 | 23582000 | 35350000
14070 |  | VEHICLES | 15 | 39.6% | 15000000 | 22881000 | 37881000 | 0 | 0 | 0 | 15000000 | 22881000 | 37881000 | 31593375
| 13.13.20 | Light Rail Cars | 9
13.__.__
14080 | 140880 | PROFESSIONAL SERVICES |  | 49.89% | 45000000 | 45200000 | 90200000 | 0 | 0 | 0 | 45000000 | 45200000 | 90200000 | 77423560.75
14090 | 140990 | UNALLOCATED CONTINGENCY |  | 18.56% | 4559000 | 20000000 | 24559000 | 0 | 0 | 0 | 4559000 | 20000000 | 24559000 | 21074714.375
14100 | 141010 | FINANCE CHARGES |  | 50% | 250000 | 250000 | 500000 | 0 | 0 | 0 | 250000 | 250000 | 500000 | 11000000
Total Project Cost (10 - 100) |  |  |  | 51.96% | 145568000 | 187034000 | 332602000 | 100000000 | 40000000 | 140000000 | 245568000 | 227034000 | 472602000 | 410219007.625
Note on I2: Add more tri-columns as required to show all funding.

## A4
SCHEDULE | Start Date | End Date | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
10 GUIDEWAY & TRACK ELEMENTS (route miles)
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
40 SITEWORK & SPECIAL CONDITIONS
50 SYSTEMS
60 ROW, LAND, EXISTING IMPROVEMENTS
70 VEHICLES (number)
80 PROFESSIONAL SERVICES (applies to Cats. 10-50)
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES
Revenue Ops / Closeout of Project
Before and After Study: Two years post Rev Ops
Fulfillment of the New Starts funding commitment
Completion of project close-out, resolution of claims
Note on D1: Delete unnecessary columns.